## Overview
Project Name | [project name]
Status | Finished
Start Date | 2018-04-01
End Date | 2018-06-27
Project profit | 19.93%
Primary Currency | USD
Conversion Date | 2018-05-01
Type | Client Project
Client | [client organization name]
Project Manager | [Edgeryders project manager name]
Online space(s) | [links to project online resources]
Concept reference | [link to project description]
Project budget (USD) | 34000
Project budget (EUR) | #REF!
Team | Alberto
Nadia
Noemi
John
Matthias

## Budget
S/N | Item Ref | Item | Person | Qty | Unit | Unit cost |  | Budget |  | Spent |  | Notes
[6 empty] | USD | EUR | USD | EUR | EUR | %
[8 empty] | 34000 | #REF! | 2245 | #REF!
1. |  | Community management |  |  |  |  | N/A | 14,400 | #REF! | 0 | #REF!
1.1. | community mgr | community manager | Noemi | 3 | FTEM | 4800 | #REF! | 14400 | #REF! | 0 | #REF!
2. | software dev | Software development | Matthias | 2 | FTEM | 4800 | #REF! | 9600 | #REF! | 0 | #REF!
3. |  | Travel |  |  |  |  | N/A | 723 | #REF! | 1,000 | #REF!
3.1. | travel Noemi 1 | Brussels - Singapore (return) for Noemi | Noemi | 1 | EA | 450 | #REF! | 450 | #REF! | 0 | #REF!
3.2. | travel Noemi 2 | Brussels - Geneva (return) for Noemi | Noemi | 1 | EA | 273 | #REF! | 273 | #REF! | 1000 | #REF!
4. | misc | Miscellanea |  | 1 | lump sum | 2500 | #REF! | 2500 | #REF! | 1245 | #REF!
5. | margin | Edgeryders margin |  |  |  |  | N/A | 6777 | #REF! | 0 | #REF!

## Expenses
Payment Date | Description | Budget Ref | Cost | Auth | Paid | Notes
(earliest planned) |  |  | EUR
6173
2018-06-15 | Noemi airline ticket Singapore | travel Noemi 2 | 1000 | TRUE | TRUE
2018-06-18 | Noemi hotel Singapore | travel Noemi 1 | 250 | FALSE | TRUE
2018-07-10 | Noemi salary for June | community mgr | 4800 | FALSE | FALSE
2018-07-12 | Noemi salary missing bits | community mgr | 123 | FALSE | FALSE
2018-07-14 | various purchases in shops | misc | 456 | FALSE | TRUE
2018-07-16 | various purchases in shops | misc | 789 | FALSE | TRUE

## Revenues
Invoice Date | Payment Date | Description | Revenues |  | Received | Notes
| (latest planned) |  | USD | EUR
|  |  | 33000 | #REF!
2018-04-15 | 2018-04-30 | Invoice "Milestone 1" | 8000 | #REF! | TRUE
2018-05-10 | 2018-05-22 | Invoice "Milestone 2" | 12500 | #REF! | TRUE
2018-06-24 | 2018-06-27 | Invoice "Milestone 3" | 12500 | #REF! | FALSE

## Status
Date | Status | Project Probability | Status Summary | Details Link (optional)
2018-01-01 | Idea | 15% | Had an idea. | link
2018-02-01 | Negotiating | 35% | Contacted potential client.
2018-03-01 | Dropped | 0% | Client declined.
2018-03-02 | Negotiating | 55% | Found another client to contact, looks more promising.
2018-04-01 | Active | 100% | Contract signed!
2018-05-01 | Active | 100% | Milestone 2
2018-06-27 | Finished | 100% | Milestone 3, and last invoice paid.

## ChartData1
Payment Date | Description | Cost / Revenue | Old Balance Sort Key | Old Balance | New Balance Sort Key | New Balance | Empty Column
|  | EUR |  | EUR |  | EUR
DO NOT EDIT – This sheet exists for technical reasons, automatically converting data to the format needed for the cash flow prediction chart.
2018-04-01 | Project Start |  | 1 | 0 | 2 | 0
2018-04-30 | Invoice "Milestone 1" | #REF! | 1 | 0 | 2 | #REF!
2018-05-22 | Invoice "Milestone 2" | #REF! | 1 | #REF! | 2 | #REF!
2018-06-15 | Noemi airline ticket Singapore | -1000 | 1 | #REF! | 2 | #REF!
2018-06-18 | Noemi hotel Singapore | -250 | 1 | #REF! | 2 | #REF!
2018-06-27 | Invoice "Milestone 3" | #REF! | 1 | #REF! | 2 | #REF!
2018-07-10 | Noemi salary for June | -4800 | 1 | #REF! | 2 | #REF!
2018-07-12 | Noemi salary missing bits | -123 | 1 | #REF! | 2 | #REF!
2018-07-14 | various purchases in shops | -456 | 1 | #REF! | 2 | #REF!
2018-07-16 | various purchases in shops | -789 | 1 | #REF! | 2 | #REF!
|  | 0 | 1 | #REF! | 2 | #REF!
|  | 0 | 1 | #REF! | 2 | #REF!
|  | 0 | 1 | #REF! | 2 | #REF!
|  | 0 | 1 | #REF! | 2 | #REF!
|  | 0 | 1 | #REF! | 2 | #REF!
|  | 0 | 1 | #REF! | 2 | #REF!
|  | 0 | 1 | #REF! | 2 | #REF!
|  | 0 | 1 | #REF! | 2 | #REF!
|  | 0 | 1 | #REF! | 2 | #REF!
|  | 0 | 1 | #REF! | 2 | #REF!
|  | 0 | 1 | #REF! | 2 | #REF!
|  | 0 | 1 | #REF! | 2 | #REF!
|  | 0 | 1 | #REF! | 2 | #REF!
|  | 0 | 1 | #REF! | 2 | #REF!
|  | 0 | 1 | #REF! | 2 | #REF!
|  | 0 | 1 | #REF! | 2 | #REF!
|  | 0 | 1 | #REF! | 2 | #REF!
|  | 0 | 1 | #REF! | 2 | #REF!
|  | 0 | 1 | #REF! | 2 | #REF!
|  | 0 | 1 | #REF! | 2 | #REF!
|  | 0 | 1 | #REF! | 2 | #REF!
|  | 0 | 1 | #REF! | 2 | #REF!
|  | 0 | 1 | #REF! | 2 | #REF!
|  | 0 | 1 | #REF! | 2 | #REF!
|  | 0 | 1 | #REF! | 2 | #REF!
|  | 0 | 1 | #REF! | 2 | #REF!
|  | 0 | 1 | #REF! | 2 | #REF!
|  | 0 | 1 | #REF! | 2 | #REF!
|  | 0 | 1 | #REF! | 2 | #REF!
|  | 0 | 1 | #REF! | 2 | #REF!
|  | 0 | 1 | #REF! | 2 | #REF!
|  | 0 | 1 | #REF! | 2 | #REF!
|  | 0 | 1 | #REF! | 2 | #REF!
|  | 0 | 1 | #REF! | 2 | #REF!
|  | 0 | 1 | #REF! | 2 | #REF!
|  | 0 | 1 | #REF! | 2 | #REF!
|  | 0 | 1 | #REF! | 2 | #REF!
|  | 0 | 1 | #REF! | 2 | #REF!
|  | 0 | 1 | #REF! | 2 | #REF!
|  | 0 | 1 | #REF! | 2 | #REF!
|  | 0 | 1 | #REF! | 2 | #REF!
|  | 0 | 1 | #REF! | 2 | #REF!
|  | 0 | 1 | #REF! | 2 | #REF!
|  | 0 | 1 | #REF! | 2 | #REF!
|  | 0 | 1 | #REF! | 2 | #REF!
|  | 0 | 1 | #REF! | 2 | #REF!
|  | 0 | 1 | #REF! | 2 | #REF!
|  | 0 | 1 | #REF! | 2 | #REF!
|  | 0 | 1 | #REF! | 2 | #REF!
|  | 0 | 1 | #REF! | 2 | #REF!
|  | 0 | 1 | #REF! | 2 | #REF!
|  | 0 | 1 | #REF! | 2 | #REF!
|  | 0 | 1 | #REF! | 2 | #REF!
|  | 0 | 1 | #REF! | 2 | #REF!
|  | 0 | 1 | #REF! | 2 | #REF!
|  | 0 | 1 | #REF! | 2 | #REF!
|  | 0 | 1 | #REF! | 2 | #REF!
|  | 0 | 1 | #REF! | 2 | #REF!
|  | 0 | 1 | #REF! | 2 | #REF!
|  | 0 | 1 | #REF! | 2 | #REF!
|  | 0 | 1 | #REF! | 2 | #REF!
|  | 0 | 1 | #REF! | 2 | #REF!
|  | 0 | 1 | #REF! | 2 | #REF!
|  | 0 | 1 | #REF! | 2 | #REF!
|  | 0 | 1 | #REF! | 2 | #REF!
|  | 0 | 1 | #REF! | 2 | #REF!
|  | 0 | 1 | #REF! | 2 | #REF!
|  | 0 | 1 | #REF! | 2 | #REF!
|  | 0 | 1 | #REF! | 2 | #REF!
|  | 0 | 1 | #REF! | 2 | #REF!
|  | 0 | 1 | #REF! | 2 | #REF!
|  | 0 | 1 | #REF! | 2 | #REF!
|  | 0 | 1 | #REF! | 2 | #REF!
|  | 0 | 1 | #REF! | 2 | #REF!
|  | 0 | 1 | #REF! | 2 | #REF!
|  | 0 | 1 | #REF! | 2 | #REF!
|  | 0 | 1 | #REF! | 2 | #REF!
|  | 0 | 1 | #REF! | 2 | #REF!
|  | 0 | 1 | #REF! | 2 | #REF!
|  | 0 | 1 | #REF! | 2 | #REF!
|  | 0 | 1 | #REF! | 2 | #REF!
|  | 0 | 1 | #REF! | 2 | #REF!
|  | 0 | 1 | #REF! | 2 | #REF!
|  | 0 | 1 | #REF! | 2 | #REF!
|  | 0 | 1 | #REF! | 2 | #REF!
|  | 0 | 1 | #REF! | 2 | #REF!
|  | 0 | 1 | #REF! | 2 | #REF!
|  | 0 | 1 | #REF! | 2 | #REF!
|  | 0 | 1 | #REF! | 2 | #REF!
|  | 0 | 1 | #REF! | 2 | #REF!
|  | 0 | 1 | #REF! | 2 | #REF!

## ChartData2
Payment Date | Balance Sort Key | Description | Balance
EUR
DO NOT EDIT – This sheet exists for technical reasons, automatically converting data to the format needed for the cash flow prediction chart.
2018-04-01 | 1 |  | 0
2018-04-01 | 2 | Project Start | 0
2018-04-30 | 1 |  | 0
2018-04-30 | 2 | Invoice "Milestone 1" | #REF!
2018-05-22 | 1 |  | #REF!
2018-05-22 | 2 | Invoice "Milestone 2" | #REF!
2018-06-15 | 1 |  | #REF!
2018-06-15 | 2 | Noemi airline ticket Singapore | #REF!
2018-06-18 | 1 |  | #REF!
2018-06-18 | 2 | Noemi hotel Singapore | #REF!
2018-06-27 | 1 |  | #REF!
2018-06-27 | 2 | Invoice "Milestone 3" | #REF!
2018-07-10 | 1 |  | #REF!
2018-07-10 | 2 | Noemi salary for June | #REF!
2018-07-12 | 1 |  | #REF!
2018-07-12 | 2 | Noemi salary missing bits | #REF!
2018-07-14 | 1 |  | #REF!
2018-07-14 | 2 | various purchases in shops | #REF!
2018-07-16 | 1 |  | #REF!
2018-07-16 | 2 | various purchases in shops | #REF!
| 1 |  | #REF!
| 1 |  | #REF!
| 1 |  | #REF!
| 1 |  | #REF!
| 1 |  | #REF!
| 1 |  | #REF!
| 1 |  | #REF!
| 1 |  | #REF!
| 1 |  | #REF!
| 1 |  | #REF!
| 1 |  | #REF!
| 1 |  | #REF!
| 1 |  | #REF!
| 1 |  | #REF!
| 1 |  | #REF!
| 1 |  | #REF!
| 1 |  | #REF!
| 1 |  | #REF!
| 1 |  | #REF!
| 1 |  | #REF!
| 1 |  | #REF!
| 1 |  | #REF!
| 1 |  | #REF!
| 1 |  | #REF!
| 1 |  | #REF!
| 1 |  | #REF!
| 1 |  | #REF!
| 1 |  | #REF!
| 1 |  | #REF!
| 1 |  | #REF!
| 1 |  | #REF!
| 1 |  | #REF!
| 1 |  | #REF!
| 1 |  | #REF!
| 1 |  | #REF!
| 1 |  | #REF!
| 1 |  | #REF!
| 1 |  | #REF!
| 1 |  | #REF!
| 1 |  | #REF!
| 1 |  | #REF!
| 1 |  | #REF!
| 1 |  | #REF!
| 1 |  | #REF!
| 1 |  | #REF!
| 1 |  | #REF!
| 1 |  | #REF!
| 1 |  | #REF!
| 1 |  | #REF!
| 1 |  | #REF!
| 1 |  | #REF!
| 1 |  | #REF!
| 1 |  | #REF!
| 1 |  | #REF!
| 1 |  | #REF!
| 1 |  | #REF!
| 1 |  | #REF!
| 1 |  | #REF!
| 1 |  | #REF!
| 1 |  | #REF!
| 1 |  | #REF!
| 1 |  | #REF!
| 1 |  | #REF!
| 1 |  | #REF!
| 1 |  | #REF!
| 1 |  | #REF!
| 1 |  | #REF!
| 1 |  | #REF!
| 1 |  | #REF!
| 1 |  | #REF!
| 1 |  | #REF!
| 1 |  | #REF!
| 1 |  | #REF!
| 1 |  | #REF!
| 1 |  | #REF!
| 1 |  | #REF!
| 1 |  | #REF!
| 1 |  | #REF!
| 1 |  | #REF!
| 1 |  | #REF!
| 1 |  | #REF!
| 1 |  | #REF!
| 1 |  | #REF!
| 1 |  | #REF!
| 1 |  | #REF!
| 1 |  | #REF!
| 1 |  | #REF!
| 1 |  | #REF!
| 1 |  | #REF!
| 1 |  | #REF!
| 1 |  | #REF!
| 2 |  | #REF!
| 2 |  | #REF!
| 2 |  | #REF!
| 2 |  | #REF!
| 2 |  | #REF!
| 2 |  | #REF!
| 2 |  | #REF!
| 2 |  | #REF!
| 2 |  | #REF!
| 2 |  | #REF!
| 2 |  | #REF!
| 2 |  | #REF!
| 2 |  | #REF!
| 2 |  | #REF!
| 2 |  | #REF!
| 2 |  | #REF!
| 2 |  | #REF!
| 2 |  | #REF!
| 2 |  | #REF!
| 2 |  | #REF!
| 2 |  | #REF!
| 2 |  | #REF!
| 2 |  | #REF!
| 2 |  | #REF!
| 2 |  | #REF!
| 2 |  | #REF!
| 2 |  | #REF!
| 2 |  | #REF!
| 2 |  | #REF!
| 2 |  | #REF!
| 2 |  | #REF!
| 2 |  | #REF!
| 2 |  | #REF!
| 2 |  | #REF!
| 2 |  | #REF!
| 2 |  | #REF!
| 2 |  | #REF!
| 2 |  | #REF!
| 2 |  | #REF!
| 2 |  | #REF!
| 2 |  | #REF!
| 2 |  | #REF!
| 2 |  | #REF!
| 2 |  | #REF!
| 2 |  | #REF!
| 2 |  | #REF!
| 2 |  | #REF!
| 2 |  | #REF!
| 2 |  | #REF!
| 2 |  | #REF!
| 2 |  | #REF!
| 2 |  | #REF!
| 2 |  | #REF!
| 2 |  | #REF!
| 2 |  | #REF!
| 2 |  | #REF!
| 2 |  | #REF!
| 2 |  | #REF!
| 2 |  | #REF!
| 2 |  | #REF!
| 2 |  | #REF!
| 2 |  | #REF!
| 2 |  | #REF!
| 2 |  | #REF!
| 2 |  | #REF!
| 2 |  | #REF!
| 2 |  | #REF!
| 2 |  | #REF!
| 2 |  | #REF!
| 2 |  | #REF!
| 2 |  | #REF!
| 2 |  | #REF!
| 2 |  | #REF!
| 2 |  | #REF!
| 2 |  | #REF!
| 2 |  | #REF!
| 2 |  | #REF!
| 2 |  | #REF!
| 2 |  | #REF!
| 2 |  | #REF!
| 2 |  | #REF!
| 2 |  | #REF!
| 2 |  | #REF!
| 2 |  | #REF!
| 2 |  | #REF!
| 2 |  | #REF!
| 2 |  | #REF!
| 2 |  | #REF!
| 2 |  | #REF!
| 2 |  | #REF!
| 2 |  | #REF!